CITY OF UNALASKA

Request for Proposals
Eagles View Elementary Playground & Soccer Field Improvement Project

City of Unalaska- Parks, Culture & Recreation – Eagles View Elementary school

1. Project Overview

The City of Unalaska is requesting proposals from qualified contractors for the Eagles View Elementary Playground and Soccer Field Improvement Project.

This project will involve the reconfiguration of three (3) existing playground areas into two (2) updated playgrounds and the upgrade of the existing soccer field to artificial turf with associated drainage and edging improvements.

The goal of this project is to modernize playground facilities, improve safety and accessibility, and provide a durable all-weather soccer field for school and community use.

The project is located at Eagles View Elementary School in Unalaska, Alaska.

Substantial completion is required by August 10, 2026.

2. Project Scope of Work

The contractor shall provide all labor, materials, equipment, supervision, and services necessary to complete the project in accordance with the project plans, specifications, and manufacturer installation requirements.

Work includes, but is not limited to, the following:

Site Protection and Security

- Furnish and install temporary security fencing and site protection measures as necessary to prevent theft, vandalism, or injury during construction.

- Protect existing site infrastructure including fencing, pavement, signage, and structures.
The contractor shall be fully responsible for repair or replacement of any site elements damaged during construction.

Soccer Field Improvements

- Remove and properly dispose of the organic layer from the existing soccer field.

- Perform grading and preparation of the field subgrade.

- Install subgrade drainage infrastructure in accordance with the project plans.

- Install concrete curb edging and nailer boards required for artificial turf installation.

- Install wear course material in preparation for the installation of owner-supplied artificial turf, which will be installed by others.

Playground Site Preparation

- Perform site grading and subgrade preparation for playground areas in accordance with the plans.

- Install required drainage infrastructure, gravel base materials, and curbing.

Concrete Work

- Construct new concrete curbing and edging in accordance with the project plans.

Playground Equipment Installation

- Layout and install owner-furnished playground equipment and site furnishings in accordance with:

- Project plans

- Manufacturer installation requirements

- Applicable playground safety standards.

Playground Surfacing

- Install owner-furnished interlocking playground tile surfacing in accordance with manufacturer specifications and project plans.

Landscaping and Restoration

- Hydroseed and restore all disturbed lawn areas resulting from construction activities.

Material Testing

- Contractor shall provide third-party material testing, including:

- Subgrade compaction testing to 95% compaction in 6-inch lifts

- Concrete testing for 3500 PSI concrete.

Construction Survey

- Contractor shall provide construction surveying and layout services necessary to construct the project in accordance with the project plans.

3. Contractor Responsibilities

The selected contractor shall:

- Provide all required labor, supervision, materials, and equipment

- Coordinate work with the City of Unalaska and project stakeholders

- Follow all manufacturer installation requirements

- Comply with all applicable building, safety, and accessibility codes

- Maintain a safe and secure work site

- Maintain construction schedule to meet the August 10, 2026 completion deadline

4. Applicable Standards

All work shall comply with applicable standards including but not limited to:

- ASTM Playground Safety Standards

- CPSC Public Playground Safety Handbook

- ADA Accessibility Guidelines

- Manufacturer installation requirements

- Applicable State of Alaska and City of Unalaska construction standards.

5. Proposal Requirements

Proposals shall include the following:

- Contractor qualifications and experience

- Relevant playground or park construction projects

- Project approach and methodology

- Construction schedule

- Cost proposal

- References for similar completed projects

- Proof of required licensing and insurance

6. Evaluation Criteria

Proposals will be evaluated based on:

- Contractor qualifications and experience

- Experience with playground installation and site work

- Project schedule and ability to meet completion deadline

- Cost proposal

- References and past project performance

7. General notes

- All work shall be in conformance with 2020 AK DOT Standard Specifications.

- Contractor is responsible for protecting existing pavement, landscaping, and structures from damage during installation and for repairing or replacing site elements damaged during installation.

- Contractor is responsible for providing work area fencing, maintaining pedestrian safety, and providing signage during construction. 2. Utilities: Contractor is responsible for locating and avoiding existing utilities above and below ground during construction activities. It is the contractor's responsibility to order utility locates prior to breaking ground and to repair or replace utilities damaged during construction. 3. This drawing shall not be altered in any way. If changes are required, please contact your Great Western Recreation sales representative.

- It is the contractor's responsibility to verify and maintain all C.P.S.C. playground safety requirements for heights, clearances, and distances related to equipment, safety surfacing, shade structures, and materials. Installation of concrete curb and bike trail by others after installation of shade structure.

- Smooth out, topsoil, and seed all non-paved areas disturbed during construction.

7. Project Timeline

RFP Release: March 13, 2026
Proposal Deadline: April 13, 2026
Contract Award: April 27, 2026
Construction Start: June 1, 2026
Substantial Completion: August 10, 2026

8. Submission Instructions and Deadline

Proposals must be received by the Unalaska City Clerk no later than 5:00 p.m. Alaska Time on Monday, April 13, 2026. Proposals may be delivered via email, U. S. Mail, other delivery service or by hand delivery.  Late submissions will not be considered.

City Clerk

City of Unalaska

43 Raven Way

P. O. Box 610

Unalaska, AK 99685

Email: emagdaong@unalaska.gov

Contact Information: For questions or further information about this RFP, please contact:

Jolene Longo
Business and Operations Manager

City of Unalaska

Parks, Culture & Recreation

P. O. Box 610

Unalaska, Ak 99685

(907) 581-1297

Email: jlongo@unalaska.gov

Attachments:

- Eagle’s View sheet Set March 12.pdf

- 2-5 Installation Combined.pdf

- 5-12 Installation Combined.pdf

- Install Hours and Concrete for footings.pdf

- Custom Installation instructions.pdf